## Sprint-3-Backlog
No. | Description | Acceptance Criteria | Priority | Feature | Story point | Assignee
US_S3_01 | As a data engineer, I want the ETL pipeline to complete extraction and transformation within a reasonable time threshold so that the system is practical for real-world workloads. | * Pipeline completes within defined time threshold * Performance improves compared to previous runs * Bottlenecks are identified and optimized * Execution metrics are logged * Data accuracy remains unaffected | High | Pipeline Reliability & Performance | 11 | Orges Velia
US_S3_02 | As a compliance officer, I want API keys and database credentials to be stored securely so that sensitive data is not exposed. | * Credentials are not hardcoded * Sensitive data is not logged * Secure storage mechanism is used * Access is restricted properly * Data exposure risks are minimized | High | Security & Resource Optimization | 5 | Orges Velia
US_S3_03 | As a developer, I want the pipeline to be modular and independently testable so that changes can be made without affecting the entire system. | * Pipeline components are modular * Changes do not break other modules * Code is reusable and clean * New features can be added easily * Documentation is updated | High | Security & Resource Optimization | 8 | Orges Velia
US_S3_04 | As a data steward, I want every agent action to be logged with execution details so that pipeline runs can be audited. | * All actions are logged with timestamps * Input/output summaries are stored * Logs are retrievable * Audit trail is complete * Logs are structured and readable | High | Traceability & Audit Logging | 8 | kn51033n
US_S3_05 | As a data engineer, I want the pipeline to handle large datasets efficiently so that performance remains stable as data grows. | * Pipeline handles increasing dataset sizes * Performance degradation is minimal * System remains stable under load * No crashes occur * Resource usage is controlled | Medium | Pipeline Reliability & Performance | 13 | Tenzing Salaka
US_S3_06 | As a user, I want to validate dataset quality so that I can detect issues before processing. | * Missing values are detected * Duplicate records are identified * Data types are validated * Validation summary is generated * Errors are clearly reported | Medium | Data Quality & Health Insights | 8 | Priya Prajapati
US_S3_07 | As a user, I want to rate pipeline runs and provide feedback so that the system can improve over time. | * Users can submit ratings * Feedback is stored successfully * Comments can be added * Feedback is linked to runs * UI is easy to use | Medium | User Feedback & Learning Loop | 5 | Shreya Kuvalekar
US_S3_08 | As a user, I want to connect a database to the system so that I can ingest structured data. | * Database connection is successful * Data can be fetched correctly * Connection errors are handled * Data is validated * Logs capture interaction | High | Data Source Integration | 8 | Orges Velia
US_S3_09 | As a user, I want to connect API-based datasets so that I can ingest external data into the system. | * API connections work correctly * Data is parsed successfully * Errors are handled properly * Data validation is applied * API interactions are logged | Medium | Data Source Integration | 8 | Tenzing Salaka